InBCT 2.2: Mukautuvat käyttöliittymät: psykologinen lähestymistapa epätyypillisten käyttäjien personointiin

Yleistä

Mukautuvat käyttöliittymät –projektissa rakennetaan virtuaalinen tutkimus- ja kehittämisympäristö. Järjestelmän helppokäyttöisillä työkaluilla voidaan yhdistää erilaisia AI tekniikoita ja tuottaa AI-pohjaisia mukautuvia e-oppimis- ja e-arviointimateriaaleja käytettäväksi internetin välityksellä. Järjestelmän testaus, validointi ja viimeistely toteutetaan epätyypillisten käyttäjien personoinnin tutkimuksena, erityisesti adaptiivisina e-oppimiskokeiluina sellaisilla henkilöillä, joilla muutoin on todettu olevan vaikeuksia oppia samankaltaisia sisältöjä.

Tavoitteet vs. tulokset

Ohjelman ensimmäinen prototyyppi valmistuu suunnitellun aikataulun mukaisesti syksyllä 2002. Tällä hetkellä ohjelmaan integroidaan ES ja IRT –tekniikoita. Ensimmäiset kenttäkokeilut, joissa selvitetään kognitiivisissa strategioissa ilmeneviä yksilöllisiä eroja, lähtevät käyntiin myös vuoden 2002 aikana.

Tiedon louhinnan, piirre-erottelumenetelmien, luokittelumallien ja monikriteerisen päätöksenteon tekniikoisen sisällyttäminen ohjelmaan ovat vuoden 2003 toiminnan päätavoitteet

Osallistuvat yritykset

Yritykset eivät ole osallistuneet projektiin vielä prototyypin valmistusvaiheessa.

Tunnetut riskit ja ongelmat

Useille tavoitelluille tutkijoille/kehittäjille adaptiivisuus sekä automaisoitujen arviointiprosessien alue saattaa olla liian vieras, mikä estää työkalun leviämisen tutkijoiden /kehittäjien keskuuteen huolimatta helppokäyttöisistä työkaluista. Riskin minimoimiseksi tarvitaan erityisiä demo/ käsikirja /koulutus tukipalveluja.

Internetin tuottaman mittausvirheen riittämätön kontrolloitavuus saattaa rajoittaa joidenkin psykometristen personointitehtävien käytettävyyttä supistaen ohjelman käyttölaajuutta. Kontrollointimenetelmien tutkimusta tarvitaan.

Yhteistyömahdollisuudet

Tutkimus liittyen

moniulotteiseen tietoon ja AI tekniikoihin perustuvaan mukauttamiseen sekä näihin yhteydessä olevat AI ja tilastolliset tekniikat

psykologiseen tietoon perustuvaan personointiin

Suorat keskustelut tutkimusyhteistyöstä osallistuvien yritysten kanssa aloitetaan 2003. Yhteyshenkilö: tekninen vastaava Janne Ylinen

Kiinnostusalueet

| Tekniikka | Mukautuvuus | Psykologia |
| --- | --- | --- |
| Java | Asiantuntijajärjestelmät (ES) | Moniulotteinen tieto |
| Hajautetut järjestelmät | Monikriteerinen päätöksenteko | Kognitiivinen prosessointi |
| Komentokokonaisuuksien visuaalinen rakentaminen | Piirre-erottelu ja luokittelu | Personointi |
| Neteksperimentaatio | IRT | E-oppinen |
| e-oppimisympäristöt | Tiedon louhinta | (E)-oppimisvaikeudet |

Henkilöt

Janne Ylinen, tekninen vastaava; Oleksander Maslov, suunnittelija; Iryna Yevseyeva,suunnittelija; Mykola Pechenizkiy, tohtoriopiskelija; Pekka Räsänen, neuropsykologi,projektivastaava

Presentations and publications of the project

Pechenizkiy, M. (2001). Computerized Adaptive Psychological Testing – A Personalisation Perspective. In proceedings of the 1st international conference on Psychology and the internet: A European perspective, Farnborough, UK,.

Pechenizkiy, M., & Maslov, O. (submitted)  Computerized Adaptive Psychological System. International Conference on the Education and Virtuality. Yalta, Ukraine.

Räsänen, P., & Pechenizkiy, M. (2001) ARITES & NEURE –  tools for experiment generation, research and assessment via internet connection. Program demonstrations at the 1st congress on Psychology and the internet: A European perspective. Farnborough, UK.

Yevseyeva, I. (2002). Computerised Estimation of Children's Learning Abilities. A presentation at the congress on Information Technology in Education and Management. New Kahovka, Ukraine.

Yevseyeva, I. (2002). Estimation of Learning Abilities Utilising MCDM Tools. A presentation at 56th Meeting of the European Working Group "Multiple Criteria Decision Aiding". Coimbra, Portugal.

Tsymbal A., Puuronen S., Pechenizkiy, M., Baumgarten, M., & Patterson, D. (2002). Eigenvector-based Feature Extraction for Classification. Proceedings of the 15th International FLAIRS Conference, Florida, USA, pp 354-358.

2.2. Adaptive user interfaces: psychological approach for atypical users personalization

Overview

The Adaptive user interfaces -project develops a virtual environment for R&D with build-in easy-to-use constructing tools. These tools integrate a number of AI techniques and enable building AI-based adaptive e-learning and e-assessment materials to be used via the internet. The testing, validation and refinement of the system will be done in the context of personalization of atypical users, including studies on adaptive e-learning for those who otherwise have exhibited difficulties in learning similar contents.

Objectives vs. results

The first prototype of the program will be accomplished according to the planned schedule during the autumn 2002. The ES and IRT techniques are subject of implementation and integration at the moment and likewise the first field experiments focused on analyses of individual differences in cognitive strategies will be started during2002.

The implementation of data mining techniques, including a set of feature extraction methods, classification model and MC DM techniques and their integration into the e-learning environment will be the main goal of the year 2003.

Participating companies

Companies have not yet participated in the development work of the prototype.

Known risks and problems

Some aimed end-users of the system (among the researchers and developers of the e-learning contents) have not expertise in the area of adaptivity and personalization of automated assessment processes. Thus, there is a possibility that “spreading around” of the developed tools among researchers /developers will be hindered despite of theeasy-to-use properties. In order to minimize this risk the special demos/ manuals/ brief coursed need to be produced.

The measurement error inflicted by internet can not be sufficiently controlled for certain psychometric personalization tasks limiting the usability of the program. Research on methodologies to control these errors is needed.

Co-operation possibilities

Research on adaptivity and personalisation based on multidimensional data, including psychological data, and AI and statistical techniques

Direct discussion about research (and development) co-operation with participating companies will start in 2003. Contact person: technical manager Janne Ylinen.

Fields of interest

| Technology | Adaptivity | Psychology |
| --- | --- | --- |
| Java | Expert systems | Multidimensional data |
| Distributed systems | Multicriteria decision making | Cognitive processing |
| Visual constructor of scripts | Feature extraction & Classification | Personalization |
| Netexperimentation | Item response theory | E-learning |
| E-learning environment | Data mining | (E)-learning disabilities |

Staff

Janne Ylinen, technical manager; Oleksander Maslov, developer; Iryna Yevseyeva, developer; Mykola Pechenizkiy,  PhD student; Pekka Räsänen, neuropsychologist, project manager

Presentations and publications of the project

Pechenizkiy, M. (2001). Computerized Adaptive Psychological Testing – A Personalisation Perspective. In proceedings of the 1st international conference on Psychology and the internet: A European perspective, Farnborough, UK,.

Pechenizkiy, M., & Maslov, O. (accepted to)  Computerized Adaptive Psychological System. International Conference on the Education and Virtuality. Yalta, Ukraine.

Räsänen, P., & Pechenizkiy, M. (2001) ARITES & NEURE –  tools for experiment generation, research and assessment via internet connection. Program demonstrations at the 1st congress on Psychology and the internet: A European perspective. Farnborough, UK.

Yevseyeva, I. (2002). Computerised Estimation of Children's Learning Abilities. A presentation at the congress on Information Technology in Education and Management. New Kahovka, Ukraine.

Yevseyeva, I. (2002). Estimation of Learning Abilities Utilising MCDM Tools. A presentation at 56th Meeting of the European Working Group "Multiple Criteria Decision Aiding". Coimbra, Portugal.

Tsymbal A., Puuronen S., Pechenizkiy, M., Baumgarten, M., & Patterson, D. (2002). Eigenvector-based Feature Extraction for Classification. Proceedings of the 15th International FLAIRS Conference, Florida, USA, pp 354-358.