InBCT 2.3: The cognitions of the users

Project has started with work on the previous knowledge about transfer and learning phenomena. The outcome of the first period is a manuscript on cognitive transfer, which should be submittable in a weeks time and a larger manuscript on the phenomenon of learning. The latter shall be submitted in the beginning of the next year. In addition, three other manuscripts have been submitted partly joined with people in other projects.

Experimental work has started. For this purpose Pauli Salo has programmed an experimental environment in which one can quite freely investigate problems of transfer. Sascha Helfenstein shall work with emotional transfer investigating the commitments within Linux society.  In addition, COMAS student Marketta Niemelä, working under the supervision of Pertti Saariluoma, is conducting experiments relevant to this project and partly (i.e., subjects) financed by the project.

Major risks: The main risk of this project is failure in creating effective and working connection between everyday research problems of participating enterprises. It is vitally important that communication channels can be effectively improved.

So far this has not been essential because it is always necessary to read oneself into the topic. However, there is a possibility that this issue becomes an increasingly more difficult problem.

Future hopes: At the moment experimental work is starting normally. However, a closer connection between enterprises would be important. However, I think that in addition to standard usability themes it would be interesting and important to apply the developed conceptual and theoretical system also issues such as marketing to get a wider perspective to the problems.