InBCT 1.2.

PRUDETEA The Psychological basis of tRUst and DEvelopment of TEchnological Applications (PRUDETEA-project) Luottamuksen psykologiset perusteet ja teknologian kehittäminen

Team Leaders: Dr. Hannakaisa Isomäki, Department of Computer Science and Information Systems and

Dr. Marja Kokkonen, Department of Psychology

Research Assistants: Anni Tirkkonen, Emmi Ignatius, Jani Ruotsalainen

### Progress to Date

The PRUDETEA project examines the emotion of trust among people, and the ability of modern information and communication technology (ICT) to convey the emotion of trust between humans and technology, as well as between humans in technological environments. The emphasis of research has been during 2002 on the psychological basis of trust, and during 2003 on the individual differences in experiencing trust in human-technology interaction. The project has followed the previously presented research plan, and has proceeded as follows:

March-May 2002:  literature review on trust, a search and selection of the appropriate measures of trust, consultation with other researchers/research groups.

June 2002:  English-Finnish translation and testing of the trust measures, development of the final measurement techniques (both electronic and paper-and-pencil versions), contact with two participating IT-companies, writing of the review article on trust.

July 2002: data collection in two IT-companies, saving data, submission of the review article on psychological trust for publication (Ignatius & Kokkonen: Psykologinen luottamus: riskinottoa ja odotuksia)

August 2002:  preparations for collecting data in two other additional organizations, planning for our collaboration with the University of Porthsmouth, U.K.

September 2002:  data collection in two additional organization starts, saving data, analysis of the IT-data begins.

October-November 2002: data collection in Porthsmouth will start (Jani Ruotsalainen), pro gradu studies on trust will begin (Emmi Ignatius), feedback for IT-companies. The second phase of research begins by collecting data.

December 2002:  evaluation and planning for 2003

Cooperation with Organizations

The PRUDETEA-project has successfully collected data from two IT-companies, and is starting data collection in two educational institutions. Scientific collaboration will also take place with the Department of Psychology, University of Portsmouth, U.K.

### InBCT 1.2

### Interest Areas

Human-computer interaction; the psychology of trust: risk-taking and expectations; trust, burn-out and job satisfaction; human adaptation in technological environments; the dynamics of trust in human-computer interaction; user interface design.

Luottamuksen psykologiset perusteet ja teknologian kehittäminen

Projektissa tutkitaan uuden informaatio- ja kommunikaatioteknologian kykyä välittää luottamuksen tunnetta sekä ihmisen ja teknologian välisessä vuorovaikutuksessa että ihmisten välillä teknologisissa ympäristöissä. Tavoitteena on löytää teknologian kehittämiskohteita.

Projekti on kolmevuotinen. Ensimmäisenä vuonna tutkimus keskittyy luottamuksen psykologisen perustan analyysiin. Toisen projektivuoden aikana analyysin painopistealueina ovat luottamuksen tunteen kokemisen yksilölliset erot ihminen-teknologia vuorovaikutuksessa sekä luottamuksen tunteen dynamiikka erilaisissa teknologisissa ympäristöissä. Kolmantena vuonna selvitetään luottamuksen tunteen kokemista ihmisten välisessä teknologiavälitteisessä vuorovaikutuksessa.

Tutkimus toteutetaan yhteistyössä suomalaisten IT-yritysten sekä suomalaisten ja englantilaisen koulujen kanssa.